## 1. Role Matrix
ROLE MATRIX — Who Does What, Which KPI Metrics Apply, and What Reports Show
This sheet shows every project role in the PMS, their responsibilities, which KPI metrics apply to them, and which report tabs reflect their data. Use the role-specific scenario sheets (tabs 3–7) to see exactly what data to enter for each role.
Project Role | System Role (typical) | Primary Responsibility | Key Actions in PMS | KPI Metrics That Apply (and scoring type) | Report Tabs That Show Their Data | Who Can View Their KPI? | Auto-Scored Metrics (9) | Manual-Scored Metrics (3)
PROJECT MANAGER | ADMIN or EMPLOYEE | Plan sprints, assign work, manage timelines, approve leave & timesheets | • Create project & add members • Create sprint, set sprint goal • Create work items, assign, set due dates & story points • Approve leave requests • Approve timesheets • Enter monthly KPI scores for team | All 13 metrics apply to PM individually. As role: enables team metrics by entering due dates, story points, estimated hours. • Sprint Reliability ✦ • Delivery Timeliness ✦ • Estimation Accuracy ✦ • Throughput ✦ • Rework Ratio ✦ • Defect Leakage ✦ • Engineering Hygiene ✎ • Dependency & Agile ✦ • Reporting & Docs ✎ • Learning Velocity 👤 • Innovation 👤 • Attendance ✦ • Positive Behaviour ✎ | All 7 report tabs (can filter by project) | Super User Admin | Sprint, Delivery, Estimation, Throughput, Rework, Defect, Dependency, Attendance | Engineering Hygiene, Reporting & Docs, Positive Behaviour
TEAM LEAD | ADMIN or EMPLOYEE | Technical oversight, code reviews, mentoring team | • Review & merge PRs • Set estimated hours on items • Verify completed items before QA_DONE • Log timesheet daily • Assist in sprint planning • Log learning & innovation | All 13 metrics apply — same as Developer but Admin can also view team KPIs. (Same list as PM above) | All 7 report tabs | Super User Admin | Sprint, Delivery, Estimation, Throughput, Rework, Defect, Dependency, Attendance | Engineering Hygiene, Reporting & Docs, Positive Behaviour
DEVELOPER | EMPLOYEE | Build features, fix bugs, log time daily | • Move items from TODO → IN_PROGRESS → QA_DONE • Log timesheet hours daily against each work item • Set status to BLOCKED immediately if blocked • Log learning & innovation self-logs monthly • Submit leave requests before any absence | All 13 metrics apply. Sprint Reliability and Throughput depend on moving items to QA_DONE. (Same list as PM above) | Productivity, Allocation, Timesheet, Planned vs Actual | Super User Admin Team Lead (own record visible to self) | Sprint, Delivery, Estimation, Throughput, Rework, Defect, Dependency, Attendance | Engineering Hygiene, Reporting & Docs, Positive Behaviour
QA | EMPLOYEE | Test features, report bugs, validate fixes | • Test work items assigned to them • Create BUG work items with SEVERITY set (mandatory) • Set bugClassification on every bug • Move bugs to QA_DONE when verified/closed • Log timesheet daily • Log learning self-logs | All 13 metrics apply. Defect Leakage is based on bugs where QA is set as 'Responsible User' (not reporter). QA creating bugs against DEVELOPERS does NOT penalise the QA's own score. (Same list as PM above) | Productivity, Bugs Report, Allocation, Timesheet | Super User Admin (own record visible to self) | Sprint, Delivery, Estimation, Throughput, Rework, Defect, Dependency, Attendance | Engineering Hygiene, Reporting & Docs, Positive Behaviour
DESIGNER | EMPLOYEE | UI/UX design, prototypes, design handoffs | • Move design tasks to QA_DONE when approved • Log timesheet against design work items • Log learning (design courses, tools) • Submit leave requests | All 13 metrics apply. Sprint Reliability applies if added to sprint. Defect Leakage: design bugs where Designer is 'Responsible User'. (Same list as PM above) | Productivity, Allocation, Timesheet | Super User Admin (own record visible to self) | Sprint, Delivery, Estimation, Throughput, Rework, Defect, Dependency, Attendance | Engineering Hygiene, Reporting & Docs, Positive Behaviour
DEVOPS | EMPLOYEE | CI/CD pipelines, deployments, infrastructure | • Move DevOps tasks to QA_DONE • Log timesheet for infra/pipeline work • Log innovation (new automation, AI tools) • Submit leave requests | All 13 metrics apply. Automation & Innovation (11) is especially relevant for DevOps — pipeline scripts, AI tools, deployment improvements. (Same list as PM above) | Productivity, Allocation, Timesheet | Super User Admin (own record visible to self) | Sprint, Delivery, Estimation, Throughput, Rework, Defect, Dependency, Attendance | Engineering Hygiene, Reporting & Docs, Positive Behaviour
⚠ IMPORTANT — Defect Leakage (Metric 6): Bugs are counted against the user set as 'Responsible User' on the BUG work item — NOT the QA who created/reported it. This means: a Developer whose code had a bug gets the defect leakage score deduction. The QA who found and logged the bug is NOT penalised. Always set 'Responsible User' correctly when creating a BUG.

## 2. Super Admin & Admin View
SUPER ADMIN & ADMIN VIEW — How to Access All KPIs, Reports and Enter Manual Scores
Super User and Admin can view KPIs for every employee and access all 7 report tabs. They are also responsible for entering the 3 manual KPI scores each month. This sheet covers the exact navigation path for each task.
Task | Where to Navigate | What You'll See / Filter Options | Filters Available | Frequency | Role Required | Notes
VIEW ALL EMPLOYEES' KPI SCORES
See the KPI Appraisal dashboard for all employees | Left menu → KPI Appraisal | Table shows all active employees with: • Total score (out of 100) • Grade (A / B / C / D) • Score breakdown per category • Team average score card at top | • Period (month selector — default = current month) • Department filter • Employee search box | Monthly review | SUPER_USER or ADMIN | Employee sees only their own KPI. Admin/Super sees ALL employees.
View individual employee's full KPI breakdown | KPI Appraisal → click employee row or use Employee dropdown | Detailed breakdown of all 13 metrics: • Score bar for each metric • Points earned vs maximum • Radar chart of 5 categories | • Select employee from dropdown • Select month/period | On demand | SUPER_USER or ADMIN | Click the row to expand, or use 'Employee' dropdown at top-right to select a specific person.
ENTER MANUAL KPI SCORES (3 metrics per employee each month)
Enter Engineering Hygiene score for all employees | KPI Appraisal → click 'Enter Monthly Scores' button (top right) | A table with every employee and 3 score dropdowns: • Engineering Hygiene (0/3/5) • Reporting & Documentation (0/3/5) • Positive Behaviour (0/3/5) Enter all scores and click 'Save All Scores' | • Period auto-set to selected month • All employees listed | By 5th of every month (for previous month) | SUPER_USER or ADMIN | Scoring guide: 5 = Excellent 3 = Minor gaps / issues 0 = Violations / critical misses Default is 0 if not entered!
Verify manual scores were saved | KPI Appraisal → select employee → check individual breakdown | Engineering Hygiene, Reporting & Docs, and Positive Behaviour should each show the entered value (0, 3 or 5) | N/A | After entering scores | SUPER_USER or ADMIN | If a metric shows 0 when you expected 5, the score was not saved — re-enter it.
VIEW ALL REPORTS
Productivity Report — who is completing tasks | Left menu → Reports → Productivity tab | One row per employee showing: • Tasks completed in period • Hours logged • On-time delivery % • Productivity score | • Period (month) • Project filter | Monthly | SUPER_USER or ADMIN | Empty rows = no timesheet hours logged OR no tasks completed. Check that employees are logging timesheet daily.
Projects Report — overall project health | Left menu → Reports → Projects tab | One row per ACTIVE project showing: • Total work items • Completed items • Team size • Completion % | • Period • Project filter | Weekly / Monthly | SUPER_USER or ADMIN | Archived projects are NOT shown. Only ACTIVE projects appear.
Bugs Report — bug severity and classification breakdown | Left menu → Reports → Bugs tab | Bar charts and tables showing: • Bug count by severity (BLOCKER/CRITICAL/MAJOR/MINOR/TRIVIAL) • Bug count by classification (NEW_BUG/UI_USABILITY/PERFORMANCE etc.) • CSV export available | • Period • Project filter | Weekly / Per release | SUPER_USER or ADMIN | ⚠ Bugs without severity set are EXCLUDED from charts. Ensure QA always sets severity when creating bugs.
Allocation Report — who is over/under-allocated | Left menu → Reports → Allocation tab | One row per employee showing: • Tasks allocated • Hours logged • Utilisation % (vs 176 hrs/month max) | • Period • Project filter | Monthly | SUPER_USER or ADMIN | Utilisation over 100% = overloaded. Under 30% = underutilised. Check timesheet logging and task assignments.
Timesheet Report — hours logged and approval status | Left menu → Reports → Timesheet tab | One row per employee showing: • Total hours logged • Project they logged against • Approval status | • Period • Project filter | Weekly (approve) Monthly (review) | SUPER_USER or ADMIN | Unapproved entries appear separately. Approve weekly via Timesheet → Approval queue.
Capacity Report — availability calendar | Left menu → Reports → Capacity tab | Monthly calendar grid for every employee: • Green = available • Orange = partial (some hours) • Red = occupied (≥8 hrs) • Blue = on leave • Grey = holiday / weekend | • Period (month) | Monthly planning | SUPER_USER or ADMIN | If holidays are not configured in Settings → Holidays, those days show as available. Configure holidays at start of year.
Planned vs Actual — are estimates accurate? | Left menu → Reports → Planned vs Actual tab | One row per employee showing: • Planned hours (sum of estimatedHours) • Actual hours (sum of timesheet) • Variance % and status (over/under/on-track) | • Period • Project filter | Monthly | SUPER_USER or ADMIN | Only employees with estimatedHours > 0 OR actual hours > 0 appear. Empty report = no estimated hours set on work items.
KPI DASHBOARD FILTERS — How to drill down
Filter KPI by department | KPI Appraisal → Department dropdown (top of table) | Shows only employees in the selected department | Department selector | On demand | SUPER_USER or ADMIN | Useful when managing multiple teams — see only your team's KPI scores.
Filter KPI by period (historical months) | KPI Appraisal → Period selector (top right) | Shows KPI scores calculated for that specific month. Only data created/updated IN that month is included. | Up to 12 months back | Historical review | SUPER_USER or ADMIN | KPIs are recalculated on each page load — historical data reflects the work items created/completed in that month.
Overview Dashboard — scoped project stats for Admin/PM
View project-scoped overview (PM / TL with project memberships) | Left menu → Overview / Dashboard | Stat cards show: • Active Projects (count of YOUR projects) • Total Tasks (across YOUR projects) • Team Members (distinct members in YOUR projects) • Completed Tasks (in YOUR projects) Activity chart and announcements also scoped to your projects. | No filter needed — auto-scoped by project membership | Daily | Any user with project memberships | SUPER_USER with NO project memberships sees global system-wide stats. EMPLOYEE without PM/TL role sees personal task stats (My Projects, My Tasks).

## 3. Developer Scenarios
DEVELOPER — Role-Based KPI & Report Scenarios ¦ Detailed Data Entry Guide
Each scenario below shows the EXACT data to enter in PMS to achieve the target grade for a Developer. Follow the SETUP steps first (done by Admin/PM), then the USER ACTIONS steps. The KPI Score Breakdown shows how every point is calculated.
SCENARIO 1 ▸ Developer who completes all sprint tasks on time and logs learning — TARGET GRADE A (90 – 100 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | Create a sprint in the project | Board → Sprint Manager → New Sprint | Name: 'June Sprint' Start: Jun 1 ¦ End: Jun 30 Goal: Ship v2.0 login feature | Enables Sprint Reliability metric | —
S2 | SETUP | Create 10 TASK work items and assign to Developer | Board → New Work Item (×10) | Type: TASK Assignee: Developer Alice Story Points: 2 each Estimated Hours: 8 each Due Date: Jun 25 Sprint: June Sprint | Feeds Sprint Reliability, Delivery Timeliness, Estimation Accuracy, Throughput | —
S3 | SETUP | Activate the sprint | Board → Sprint Manager → Activate | Status → Active | Sprint items now count for Sprint Reliability | —
1 | ACTION | Move each of the 10 tasks to QA_DONE by Jun 25 (before due date) | Board → Kanban → drag each card to QA_DONE | All 10 items: status = QA_DONE completedAt = auto-set (e.g. Jun 20) (must be BEFORE dueDate Jun 25) | Sprint Reliability · Delivery Timeliness · Throughput | 15+15+10
2 | ACTION | Log 8 hours per day in timesheet (20 working days × 8 hrs = 160 hrs total) | Timesheet → Log Hours | Work Item: select the task Date: each working day Hours: 8 (10 tasks × 8 estimated hrs = 80 hrs estimated; actual logged ≈ 80 hrs → 0% variance) | Estimation Accuracy | 10
3 | ACTION | Do NOT set any item to BLOCKED status | Board (leave items as IN_PROGRESS or QA_DONE) | blockedCount = 0 totalItems = 10 blocked ratio = 0% | Dependency & Agile Management | 5
4 | ACTION | Do NOT reopen any completed (QA_DONE) item | Board | reopenCount = 0 on all items | Internal Rework Ratio | 5
5 | ACTION | Ensure no BUG with YOU as 'Responsible User' is logged | Board → Bugs (check responsibleUserId field) | No BUG work items with Alice as Responsible User | Defect Leakage | 10
6 | ACTION | Log learning activities (e.g. React course): ≥4 hours | KPI → Self-Log → Learning | Period: 2026-06 Topic: Advanced React Patterns Hours: 5 Description: Completed Udemy course | Learning Velocity | 5
7 | ACTION | Log an AI tool or automation you built this month | KPI → Self-Log → Innovation | Period: 2026-06 Title: AI Code Review Helper Impact: Reduced PR review time by 40% Type: AI_IMPLEMENTATION | Automation & Innovation | 5
8 | ACTION | Submit a leave request for any planned absence (1 day max for Grade A) | Leave Module → Submit Request | Type: Casual Leave Start: Jun 10 ¦ End: Jun 10 (Manager approves → status = APPROVED) | Attendance (1 approved day ≤ 1 → 5 pts) | 5
A1 | ADMIN | Admin enters Engineering Hygiene score: 5 | KPI Appraisal → Enter Monthly Scores | Employee: Alice Period: 2026-06 Engineering Hygiene: 5 | Engineering Hygiene metric | 5
A2 | ADMIN | Admin enters Reporting & Documentation: 5 | KPI Appraisal → Enter Monthly Scores | Reporting & Documentation: 5 | Reporting & Docs metric | 5
A3 | ADMIN | Admin enters Positive Behaviour: 5 | KPI Appraisal → Enter Monthly Scores | Positive Behaviour: 5 | Positive Behaviour metric | 5
R1 | REPORT | Check KPI Appraisal page | KPI Appraisal → select Alice → Period: Jun 2026 | Expected: 100/100 — Grade A | All 13 metrics visible in breakdown | 100
R2 | REPORT | Check Productivity Report | Reports → Productivity → Period: Jun 2026 | Alice shows: • tasksDone: 10 • hoursLogged: ~80 • onTimePct: 100% • score: high | Productivity Report | —
TOTAL | Expected Total Score: 100 / 100 → Grade A (90 – 100 pts) |  |  |  |  | 100/100
SCENARIO 2 ▸ Developer with partial sprint completion, 2 tasks reopened — TARGET GRADE B (75 – 89 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | Create 10 TASK work items in sprint, assign to Developer Bob | Board → New Work Item (×10) | Type: TASK ¦ Assignee: Bob Story Points: 2 each ¦ Estimated Hours: 8 each Due Date: Jun 25 ¦ Sprint: June Sprint | Baseline for all delivery metrics | —
1 | ACTION | Complete 8 out of 10 sprint items (move to QA_DONE before due date) | Board → Kanban → QA_DONE | 8 items QA_DONE by Jun 25 2 items remain IN_PROGRESS | Sprint Reliability: (16sp ÷ 20sp) × 15 = 12 pts Throughput: (8÷10) × 10 = 8 pts Delivery Timeliness: (8÷8) × 15 = 15 pts (only items with completedAt count) | 12+15+8
2 | ACTION | Log 8 hrs/day in timesheet (actual 70 hrs vs estimated 80 hrs) | Timesheet → Log Hours | Total hours logged: 70 Total estimated: 80 Variance: ¦70-80¦/80 = 12.5% (≤15%) | Estimation Accuracy: ≤15% variance → 10 pts | 10
3 | ACTION | Reopen 2 completed items (move back from QA_DONE to IN_PROGRESS) | Board → drag card from QA_DONE back to IN_PROGRESS | 2 items: reopenCount increments to 1 totalReopens = 2 totalCompleted = 8 | Rework Ratio: 2÷8 = 25% (>10%) → 0 pts | 0
4 | ACTION | Log 2 hours of learning only | KPI → Self-Log → Learning | Period: 2026-06 Hours: 2 (≥1 hr but <4 hrs) | Learning Velocity: ≥1 hr → 3 pts | 3
5 | ACTION | Log innovation: process improvement (not AI) | KPI → Self-Log → Innovation | Type: OTHER (not AI_IMPLEMENTATION) Title: Improved CI pipeline script | Automation & Innovation: no AI → 3 pts | 3
6 | ACTION | No blocked items, no bugs against Bob, 1 approved leave day | Board / Leave Module | blockedCount = 0 → Dependency = 5 pts No bugs with Bob as Responsible User → Defect = 10 pts 1 approved leave day → Attendance = 5 pts | Dependency + Defect Leakage + Attendance | 5+10+5
A1 | ADMIN | Admin enters manual scores: Hygiene=5, Reporting=3, Behaviour=5 | KPI Appraisal → Enter Monthly Scores | Engineering Hygiene: 5 Reporting & Docs: 3 (some missed updates) Positive Behaviour: 5 | 3 manual metrics | 5+3+5
R1 | REPORT | Check KPI Appraisal → Bob | KPI Appraisal → select Bob | Expected: 79/100 — Grade B | Score breakdown visible in radar chart | 79
TOTAL | Expected Total Score: 79 / 100 → Grade B (75 – 89 pts) |  |  |  |  | 79/100
SCENARIO 3 ▸ Newly added Developer — no tasks assigned yet (explains Grade D default) — TARGET GRADE D (Below 60 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | Add Developer Carol to the project (no tasks assigned yet) | Project → Members → Add Member | User: Carol ProjectRole: DEVELOPER No work items assigned | Carol appears in KPI list | —
! | RESULT | With NO tasks assigned and NO manual scores entered, Carol's auto score is 35/100 (Grade D). This is expected system behaviour — it does NOT mean Carol is a poor performer. | KPI Appraisal → Carol | Sprint Reliability: 0 (no sprint items) Delivery Timeliness: 0 (no items with dueDate) Estimation Accuracy: 10 (both 0 = 10) Throughput: 0 (no items) Rework Ratio: 5 (default for no completions) Defect Leakage: 10 (no bugs) Engineering Hygiene: 0 (not entered) Dependency & Agile: 5 (no items = 5) Reporting & Docs: 0 (not entered) Learning Velocity: 0 (no self-log) Innovation: 0 (no self-log) Attendance: 5 (no leaves) Positive Behaviour: 0 (not entered) ───────────────────────── Total = 35 / 100 | The KPI page shows 'N/A — Insufficient Data' badge for new members with no activity | 35
F1 | ACTION | To fix: assign tasks to Carol and have admin enter manual scores | Board → assign work items to Carol KPI → Enter Monthly Scores | Once Carol has at least 1 task assigned and manual scores entered, KPI will show a meaningful grade. | Score will increase from 35 to a fair assessment | —
TOTAL | Expected Total Score: 35 / 100 → Grade D (Below 60 pts) |  |  |  |  | 35/100

## 4. QA Scenarios
QA — Role-Based KPI & Report Scenarios ¦ Detailed Data Entry Guide
Each scenario below shows the EXACT data to enter in PMS to achieve the target grade for a Qa. Follow the SETUP steps first (done by Admin/PM), then the USER ACTIONS steps. The KPI Score Breakdown shows how every point is calculated.
SCENARIO 1 ▸ QA who tests all items, reports bugs correctly, logs learning — TARGET GRADE A (90 – 100 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | Create 8 TASK/BUG-type work items and assign to QA Priya | Board → New Work Item (×8) | Type: TASK Assignee: QA Priya Estimated Hours: 4 each Due Date: Jun 20 Story Points: 1 each | Baseline for delivery metrics | —
1 | ACTION | Move all 8 assigned items to QA_DONE before due date | Board → Kanban → QA_DONE | All 8 items: status = QA_DONE completedAt = before Jun 20 | Sprint Rel: 8÷8 × 15 = 15 pts Delivery: 8÷8 × 15 = 15 pts Throughput: 8÷8 × 10 = 10 pts | 15+15+10
2 | ACTION | Log 4 hrs/day in timesheet (actual = 32 hrs, estimated = 32 hrs) | Timesheet → Log Hours | Total hours: 32 Estimated: 32 Variance: 0% → ≤15% | Estimation Accuracy: 10 pts | 10
3 | ACTION | Create 2 MINOR bugs found during testing — set Responsible User = Developer (NOT QA) | Board → New Work Item | Type: BUG Severity: MINOR (each) Reporter: Priya (QA) Responsible User: Developer Alice (the dev whose code had the bug) Classification: NEW_BUG | ⚠ Priya is the REPORTER but Alice is RESPONSIBLE. Priya's Defect Leakage = 10 pts (no bugs against HER). Alice's Defect Leakage = 4 pts (2 MINOR bugs against her). | 10
4 | ACTION | Do NOT have any bugs where Priya is set as Responsible User | Board (verify responsibleUserId on all bugs) | Priya has 0 bugs where she is Responsible User | Defect Leakage: 0 bugs against Priya → 10 pts | 10
5 | ACTION | Log 5 hours of learning (testing tools, ISTQB preparation) | KPI → Self-Log → Learning | Period: 2026-06 Topic: ISTQB Foundation Level Prep Hours: 5 | Learning Velocity: ≥4 hrs → 5 pts | 5
6 | ACTION | Log AI tool for test automation | KPI → Self-Log → Innovation | Type: AI_IMPLEMENTATION Title: AI-Powered Test Case Generator Impact: Reduced test writing time by 50% | Automation & Innovation: AI type → 5 pts | 5
7 | ACTION | No blocked items, 1 approved leave day, no reopens | Board / Leave Module | blockedCount = 0 → 5 pts Attendance: 1 day → 5 pts Reopens = 0 → 5 pts | Dependency + Attendance + Rework | 5+5+5
A1 | ADMIN | Admin enters: Hygiene=5, Reporting=5, Behaviour=5 | KPI Appraisal → Enter Monthly Scores | All three manual metrics: 5 each | Manual metrics | 5+5+5
R1 | REPORT | Check Bugs Report for the project | Reports → Bugs → Period: Jun 2026 | Shows 2 MINOR bugs in the chart Classification: NEW_BUG × 2 (CSV export also shows classification) | Bugs Report | —
R2 | REPORT | Check Developer Alice's KPI after Priya reports bugs | KPI Appraisal → select Alice | Alice's Defect Leakage: 2 MINOR bugs totalSevere = 2 × 1 = 2 → 4 pts (not 10) | Confirms Responsible User logic is correct | —
TOTAL | Expected Total Score: 97 / 100 → Grade A (90 – 100 pts) |  |  |  |  | 97/100
SCENARIO 2 ▸ QA who reports critical bugs (penalises the responsible developer) — TARGET GRADE B (75 – 89 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | Create 6 TASK items assigned to QA Raj | Board → New Work Item (×6) | Assignee: QA Raj ¦ Story Points: 1 each Estimated Hours: 6 each ¦ Due Date: Jun 28 | Baseline setup | —
1 | ACTION | Complete 5 of 6 items before due date, 1 item missed | Board → QA_DONE | 5 items QA_DONE before Jun 28 1 item completed Jun 30 (AFTER due date) | Sprint Rel: 5÷6 × 15 = 12.5 pts Delivery: 5÷6 × 15 = 12.5 pts Throughput: 5÷6 × 10 = 8.3 pts | 12+12+8
2 | ACTION | Log 30 hrs (estimated 36 hrs → 16.6% over budget) | Timesheet → Log Hours | Total actual: 30 hrs Total estimated: 36 hrs Variance: ¦30-36¦/36 = 16.6% (16–30%) | Estimation Accuracy: 16–30% variance → 7 pts | 7
3 | ACTION | Create 1 CRITICAL bug with Developer Bob as Responsible User | Board → New Work Item | Type: BUG ¦ Severity: CRITICAL Responsible User: Developer Bob Reporter: QA Raj | Raj's Defect Leakage: 0 bugs against Raj → 10 pts Bob's Defect Leakage: 1 CRITICAL → 0 pts (criticalOrBlocker > 0 = 0 pts for Bob) | 10
4 | ACTION | Log learning: 2 hrs ¦ No innovation logged | KPI → Self-Log → Learning | Hours: 2 (≥1 but <4 hrs) No innovation log | Learning: 3 pts ¦ Innovation: 0 pts | 3+0
5 | ACTION | 1 item in BLOCKED status, 0 reopens, 1 approved leave day | Board / Leave Module | blockedCount = 1 ¦ total = 6 blocked ratio = 1/6 = 16.7% (>10%) Reopens = 0 → Rework = 5 pts Attendance = 5 pts | Dependency: >10% → 0 pts Rework: 5 pts ¦ Attendance: 5 pts | 0+5+5
A1 | ADMIN | Admin enters: Hygiene=5, Reporting=3, Behaviour=5 | KPI Appraisal → Enter Monthly Scores | Engineering Hygiene: 5 Reporting & Docs: 3 Positive Behaviour: 5 | Manual metrics | 5+3+5
TOTAL | Expected Total Score: 78 / 100 → Grade B (75 – 89 pts) |  |  |  |  | 78/100

## 5. Team Lead Scenarios
TEAM_LEAD — Role-Based KPI & Report Scenarios ¦ Detailed Data Entry Guide
Each scenario below shows the EXACT data to enter in PMS to achieve the target grade for a Team Lead. Follow the SETUP steps first (done by Admin/PM), then the USER ACTIONS steps. The KPI Score Breakdown shows how every point is calculated.
SCENARIO 1 ▸ Team Lead who sets up sprint, codes, reviews, logs learning (Grade A) — TARGET GRADE A (90 – 100 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | PM creates 8 TASK items and assigns 4 to Team Lead Suresh | Board → New Work Item (×4) | Assignee: Suresh (TEAM_LEAD) Story Points: 3 each Estimated Hours: 10 each Due Date: Jun 22 | TL also gets individual KPI — not just team oversight | —
1 | ACTION | Move all 4 TL tasks to QA_DONE before Jun 22 | Board → QA_DONE | All 4 items QA_DONE by Jun 20 | Sprint Rel: 12÷12 × 15 = 15 pts Delivery: 4÷4 × 15 = 15 pts Throughput: 4÷4 × 10 = 10 pts | 15+15+10
2 | ACTION | Log 10 hrs per item in timesheet (40 hrs total = estimated) | Timesheet → Log Hours | Actual: 40 hrs ¦ Estimated: 40 hrs Variance: 0% | Estimation Accuracy: 10 pts | 10
3 | ACTION | No items in BLOCKED, no reopens | Board | blockedCount = 0 → Dependency = 5 pts Reopens = 0 → Rework = 5 pts | Dependency + Rework | 5+5
4 | ACTION | Log 6 hrs of learning (architecture articles + internal tech talk) | KPI → Self-Log → Learning | Period: 2026-06 Topic: System Design Architecture Hours: 6 | Learning Velocity: ≥4 hrs → 5 pts | 5
5 | ACTION | Log an AI tool or automation | KPI → Self-Log → Innovation | Type: AI_IMPLEMENTATION Title: AI-based code linting assistant Impact: Cut code review time by 30% | Innovation: AI type → 5 pts | 5
6 | ACTION | Ensure no bugs have Suresh as Responsible User, 1 approved leave | Board / Leave Module | No CRITICAL/MAJOR bugs against Suresh Attendance: 1 approved day → 5 pts Defect Leakage: 10 pts | Defect Leakage + Attendance | 10+5
A1 | ADMIN | Admin enters: Hygiene=5, Reporting=5, Behaviour=5 | KPI Appraisal → Enter Monthly Scores | All three: 5 pts each | Manual metrics | 5+5+5
R1 | REPORT | Team Lead also visible in Overview Dashboard (as management user) | Overview Dashboard | Stat cards show: Active Projects: (their projects) Team Members: (members in their projects) Total Tasks: (tasks in their projects) | TL with EMPLOYEE system role now gets management view if they hold TEAM_LEAD project role | —
TOTAL | Expected Total Score: 95 / 100 → Grade A (90 – 100 pts) |  |  |  |  | 95/100

## 6. Project Manager Scenarios
PROJECT_MANAGER — Role-Based KPI & Report Scenarios ¦ Detailed Data Entry Guide
Each scenario below shows the EXACT data to enter in PMS to achieve the target grade for a Project Manager. Follow the SETUP steps first (done by Admin/PM), then the USER ACTIONS steps. The KPI Score Breakdown shows how every point is calculated.
SCENARIO 1 ▸ PM who sets up sprint correctly so team KPI auto-calculates — TARGET GRADE A (Focus on enabling team — own KPI also tracked)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
! | RESULT | The PM's most important KPI contribution is SETTING UP the correct data so the TEAM's auto-metrics work. Without due dates, story points, and estimated hours — the team gets 0 on Sprint Reliability, Delivery Timeliness, and Estimation Accuracy. | Board → Work Items | Missing due date → Delivery Timeliness = 0 for whole team Missing story points → Sprint Reliability uses count=1 (less accurate) Missing estimated hours → Estimation Accuracy = 0 | Critical — PM data entry quality determines team KPI accuracy | —
S1 | SETUP | Create Sprint with correct dates | Board → Sprint Manager → New Sprint | Name: 'Sprint 1' Start: Jun 1 End: Jun 30 Goal: Feature X launch | Enables Sprint Reliability for all sprint members | —
S2 | SETUP | Create all work items for the sprint with COMPLETE metadata | Board → New Work Item | For EVERY work item: • assigneeId: set to a team member • sprintId: this sprint • storyPoints: 1–5 (based on complexity) • estimatedHours: realistic estimate (e.g., 8 for a day's work) • dueDate: set within sprint duration • type: TASK / STORY / SUB_TASK | Enables all 4 delivery metrics for each assignee | —
S3 | SETUP | Activate the sprint at start of month | Board → Sprint Manager → Activate | Status → Active | Sprint items now qualify for Sprint Reliability calculation | —
1 | ACTION | PM completes their own assigned tasks (4 items) | Board → QA_DONE | 4 items QA_DONE before due date (PM also has 4 tasks assigned in sprint) | PM's own Sprint Rel/Delivery/Throughput 15+15+10 if all done | 15+15+10
2 | ACTION | Log 8 hrs/day in timesheet for PM's own tasks | Timesheet → Log Hours | Actual ≈ Estimated (within 15%) | PM's Estimation Accuracy: 10 pts | 10
3 | ACTION | Approve team's weekly timesheet entries | Timesheet → Approval Queue | Review and approve each Friday (Keeps Timesheet Report accurate) | Timesheet Report shows Approved status | —
4 | ACTION | Approve team leave requests within 24 hours | Leave Module → Pending | Status → APPROVED (Enables team Attendance KPI) | Team Attendance metric — leave not approved = 0 pts for employee | —
5 | ACTION | Close sprint at end of month | Board → Sprint Manager → Close | Status → Closed All remaining items move to backlog | Finalises Sprint Reliability for the month | —
6 | ACTION | PM logs learning and innovation | KPI → Self-Log → Learning / Innovation | Learning: 5 hrs (project management training) Innovation: AI_IMPLEMENTATION (project risk predictor tool) | Learning: 5 pts ¦ Innovation: 5 pts | 5+5
7 | ACTION | No blocked items, no bugs against PM, 1 approved leave | Board / Leave Module | Dependency: 5 pts ¦ Rework: 5 pts Defect: 10 pts ¦ Attendance: 5 pts | 4 auto-scored metrics | 5+5+10+5
A1 | ADMIN | Admin enters manual KPI scores for PM | KPI Appraisal → Enter Monthly Scores | Engineering Hygiene: 5 Reporting & Docs: 5 (PM keeps excellent docs) Positive Behaviour: 5 | Manual metrics | 5+5+5
A2 | ADMIN | PM enters manual KPI scores for ALL team members (by 5th of next month) | KPI Appraisal → Enter Monthly Scores | For each team member, enter: • Engineering Hygiene: 0/3/5 • Reporting & Documentation: 0/3/5 • Positive Behaviour: 0/3/5 | Without these entries, each team member loses up to 15 pts (3 metrics × 5 pts each = 15 pts of manual scoring) | —
R1 | REPORT | Check Overview Dashboard as PM | Overview Dashboard | Active Projects: count of PM's projects Team Members: members in those projects Total Tasks: tasks across those projects (NOT global system stats) | Scoped dashboard for PM/TL roles | —
R2 | REPORT | Check Projects Report | Reports → Projects | Your project shows: • All tasks created this month • Completion % • Team size | Projects Report | —
TOTAL | Expected Total Score: 90 / 100 → Grade A (Focus on enabling team — own KPI also tracked) |  |  |  |  | 90/100

## 7. Designer & DevOps
DESIGNER — Role-Based KPI & Report Scenarios ¦ Detailed Data Entry Guide
Each scenario below shows the EXACT data to enter in PMS to achieve the target grade for a Designer. Follow the SETUP steps first (done by Admin/PM), then the USER ACTIONS steps. The KPI Score Breakdown shows how every point is calculated.
SCENARIO 1 ▸ Designer — completes UI tasks, reports UI bugs, logs design learning — TARGET GRADE A (90 – 100 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | PM creates 6 design tasks and assigns to Designer Deepa | Board → New Work Item (×6) | Type: TASK Assignee: Deepa Story Points: 2 each Estimated Hours: 6 each Due Date: Jun 22 | Baseline for delivery metrics | —
1 | ACTION | Complete all 6 design tasks (QA_DONE) before Jun 22 | Board → QA_DONE | All 6 items QA_DONE by Jun 20 | Sprint Rel: 15 pts ¦ Delivery: 15 pts ¦ Throughput: 10 pts | 15+15+10
2 | ACTION | Log 6 hrs/task in timesheet (actual 36 hrs = estimated 36 hrs) | Timesheet → Log Hours | Variance: 0% | Estimation Accuracy: 10 pts | 10
3 | ACTION | Create 1 UI_USABILITY bug (set DEVELOPER as Responsible User) | Board → New Work Item | Type: BUG ¦ Severity: MINOR Classification: UI_USABILITY Responsible User: Developer (NOT Deepa) | Deepa's Defect Leakage: 10 pts (no bugs against her) This bug appears in Bugs Report under UI_USABILITY | 10
4 | ACTION | Log learning: 5 hrs (Figma Advanced, design systems) | KPI → Self-Log → Learning | Hours: 5 → ≥4 hrs | Learning Velocity: 5 pts | 5
5 | ACTION | Log innovation: AI design tool implementation | KPI → Self-Log → Innovation | Type: AI_IMPLEMENTATION Title: AI-assisted UI mockup generator | Innovation: 5 pts | 5
6 | ACTION | No blocked items, no reopens, 1 approved leave | Board / Leave Module | Dependency: 5 pts ¦ Rework: 5 pts ¦ Attendance: 5 pts | 3 auto metrics | 5+5+5
A1 | ADMIN | Admin enters: Hygiene=5, Reporting=5, Behaviour=5 | KPI Appraisal → Enter Monthly Scores | All three: 5 pts each | Manual metrics | 5+5+5
TOTAL | Expected Total Score: 95 / 100 → Grade A (90 – 100 pts) |  |  |  |  | 95/100
SCENARIO 2 ▸ DevOps — pipeline tasks, AI automation, logging innovation — TARGET GRADE A (90 – 100 pts)
Step | Category | Action / Data to Enter | Where in PMS | Field / Value | KPI / Report Impact | Points
S1 | SETUP | PM creates 5 DevOps tasks (CI/CD, infra) and assigns to DevOps Jay | Board → New Work Item (×5) | Type: TASK Assignee: Jay (DEVOPS) Story Points: 3 each Estimated Hours: 10 each Due Date: Jun 28 | Baseline | —
1 | ACTION | Complete all 5 DevOps tasks (QA_DONE) before Jun 28 | Board → QA_DONE | All 5 completed on time | Sprint Rel: 15 pts ¦ Delivery: 15 pts ¦ Throughput: 10 pts | 15+15+10
2 | ACTION | Log 10 hrs/task in timesheet (50 hrs actual vs 50 hrs estimated) | Timesheet → Log Hours | Variance: 0% | Estimation Accuracy: 10 pts | 10
3 | ACTION | Log innovation: new AI deployment pipeline | KPI → Self-Log → Innovation | Type: AI_IMPLEMENTATION Title: AI-assisted zero-downtime deployment Impact: Deployment time reduced from 20 to 3 minutes | Innovation: AI type → 5 pts (DevOps has biggest opportunity here!) | 5
4 | ACTION | Log 4 hrs of learning (Kubernetes, cloud certifications) | KPI → Self-Log → Learning | Hours: 4 (meets ≥4 threshold exactly) | Learning Velocity: 5 pts | 5
5 | ACTION | No blocked items, no bugs against Jay, 1 approved leave | Board / Leave Module | Dependency: 5 ¦ Rework: 5 ¦ Defect: 10 ¦ Attendance: 5 | 4 auto metrics | 5+5+10+5
A1 | ADMIN | Admin enters: Hygiene=5, Reporting=5, Behaviour=5 | KPI Appraisal → Enter Monthly Scores | All three: 5 pts each | Manual metrics | 5+5+5
TOTAL | Expected Total Score: 95 / 100 → Grade A (90 – 100 pts) |  |  |  |  | 95/100

## 8. KPI Formula Reference
KPI FORMULA REFERENCE — All 13 Metrics: Exact Code Logic, Thresholds & Worked Examples
These formulas are implemented exactly as shown in backend/src/analytics/analytics.service.ts. The 'Period' is always a calendar month (YYYY-MM). Data must be CREATED within the period dates to be counted. Sprint-based projects use sprint items; non-sprint projects fall back to ALL assigned items.
# | Metric Name | Category | Max Pts | Exact Formula (from source code) | Score Thresholds | Worked Example (Grade A) | Worked Example (Grade D / 0)
1 | Sprint Reliability | Delivery & Execution | 15 | isSprintBased = sprintItems.length > 0 deliveryBase = isSprintBased ? sprintItems : allAssignedItems committed = sum(storyPoints ?? 1) for all deliveryBase items delivered = sum(storyPoints ?? 1) for deliveryBase items where status=QA_DONE score = committed=0 ? 0 : min((delivered/committed) × 15, 15) | 0% completion = 0 pts 100% completion = 15 pts (proportional) | 10 sprint items × 2sp each 8 QA_DONE × 2sp = 16sp delivered (16/20) × 15 = 12 pts | committed=0 (no sprint items, no assigned items) → 0 pts
2 | Delivery Timeliness | Delivery & Execution | 15 | itemsWithDue = assignedItems where dueDate≠null AND completedAt≠null onTime = itemsWithDue where completedAt ≤ dueDate score = itemsWithDue=0 ? 0 : min((onTime/itemsWithDue) × 15, 15) | 0 on-time = 0 pts 100% on-time = 15 pts (proportional) | 8 items with dueDate, all 8 QA_DONE before dueDate → (8/8) × 15 = 15 pts | No items have dueDate set → itemsWithDue=0 → 0 pts
3 | Estimation Accuracy | Delivery & Execution | 10 | totalEstimated = sum(estimatedHours ?? 0) for deliveryBase totalActual = sum(timesheet.hours) for deliveryBase item IDs (or all timesheet in period if no deliveryBase items) if estimated=0: return actual=0 ? 10 : 0 variance = ¦actual-estimated¦ / estimated ≤0.15→10 ¦ ≤0.30→7 ¦ ≤0.50→4 ¦ else→0 | 0% variance = 10 pts 16–30% = 7 pts 31–50% = 4 pts >50% = 0 pts | Estimated: 80 hrs ¦ Actual: 82 hrs Variance: 2/80 = 2.5% (≤15%) → 10 pts | Estimated: 80 hrs ¦ Actual: 200 hrs Variance: 120/80 = 150% (>50%) → 0 pts
4 | Throughput & Complexity | Delivery & Execution | 10 | deliveryBase = sprintItems if sprint; else allAssignedItems total = deliveryBase.length completed = deliveryBase where status=QA_DONE score = total=0 ? 0 : min((completed/total) × 10, 10) | 0% done = 0 pts 100% done = 10 pts (proportional) | 8 sprint items, all 8 QA_DONE (8/8) × 10 = 10 pts | 0 sprint items and 0 assigned items in period → 0 pts
5 | Internal Rework Ratio | Quality & Engineering Exc. | 5 | totalReopens = sum(reopenCount) for allAssignedItems totalCompleted = allAssignedItems where status=QA_DONE if totalCompleted=0: return 5 ← DEFAULT full score ratio = totalReopens / totalCompleted ratio=0→5 ¦ ratio≤0.10→3 ¦ else→0 | 0% reopen = 5 pts ≤10% reopen = 3 pts >10% reopen = 0 pts | 10 completed, 0 reopened ratio = 0 → 5 pts | 10 completed, 2 reopened ratio = 0.20 (>10%) → 0 pts
6 | Technical Defect Leakage | Quality & Engineering Exc. | 10 | bugs = workItems where type=BUG AND responsibleUserId=this_user AND createdAt in period criticalOrBlocker = count(SHOW_STOPPER/CRITICAL/BLOCKER bugs) if criticalOrBlocker > 0: return 0 minors = count(MINOR/TRIVIAL) majors = count(MAJOR) totalSevere = majors×2 + minors 0→10 ¦ 1→7 ¦ 2→4 ¦ ≥3→0 ⚠ Uses responsibleUserId NOT reporterId | 0 bugs = 10 pts 1 MINOR = 7 pts 2 MINOR = 4 pts 1 CRITICAL or 3+ MINOR = 0 pts | 0 bugs with this user as Responsible → 10 pts | 1 CRITICAL bug with this user as Responsible → 0 pts
7 | Engineering Hygiene | Quality & Engineering Exc. | 5 | MANUAL — Admin enters in KPI → Enter Monthly Scores metricId = 'engineering_hygiene' options: 5 / 3 / 0 DEFAULT = 0 if not entered | 5 = Excellent practices 3 = Minor gaps 0 = Violations or not entered by admin | Admin enters 5 (excellent code quality, linting, security) → 5 pts | Admin has not entered score yet → 0 pts (default)
8 | Dependency & Agile Mgmt | Ownership & Collaboration | 5 | blockedCount = allAssignedItems where status=BLOCKED totalItems = allAssignedItems.length if totalItems=0: return 5 ← DEFAULT full score ratio = blockedCount / totalItems ratio=0→5 ¦ ratio≤0.10→3 ¦ else→0 | 0% blocked = 5 pts ≤10% blocked = 3 pts >10% blocked = 0 pts | 10 items, 0 blocked ratio = 0 → 5 pts | 10 items, 2 blocked ratio = 0.20 (>10%) → 0 pts
9 | Reporting & Documentation | Ownership & Collaboration | 5 | MANUAL — Admin enters in KPI → Enter Monthly Scores metricId = 'reporting_documentation' options: 5 / 3 / 0 DEFAULT = 0 if not entered | 5 = Accurate, no gaps 3 = Inconsistent / delays 0 = Critical misses or not entered by admin | Admin enters 5 (all status updates on time, clear documentation) → 5 pts | Admin has not entered score yet → 0 pts (default)
10 | Learning Velocity | Growth & Innovation | 5 | learningLogs = SelfLog.learningLog where userId=this AND period=YYYY-MM totalHours = sum(hours) across those logs totalHours≥4→5 ¦ totalHours≥1→3 ¦ else→0 | ≥4 hours = 5 pts ≥1 hour = 3 pts 0 hours = 0 pts | 5 hrs logged in Self-Log → ≥4 hrs → 5 pts | No self-log learning entries for period → 0 pts
11 | Automation & Innovation | Growth & Innovation | 5 | innovationLogs = SelfLog.innovationLog where userId=this AND period=YYYY-MM if innovationLogs.length=0: return 0 hasAI = any log where type=AI_IMPLEMENTATION hasAI→5 ¦ else→3 | AI implementation = 5 pts Other improvement = 3 pts No entries = 0 pts | 1 innovation log with type=AI_IMPLEMENTATION → 5 pts | No innovation logs for period → 0 pts
12 | Attendance | Behaviour & Reliability | 5 | leaveRequests = LeaveRequest where userId=this AND status in [APPROVED,REJECTED] AND period overlaps hasRejected = any(status=REJECTED) if hasRejected: return 0 approvedDays = sum of overlap days for APPROVED leaves approvedDays>1.5→0 ¦ approvedDays>1→3 ¦ else→5 | ≤1 day approved leave = 5 pts 1 to 1.5 days = 3 pts >1.5 days OR any rejected = 0 pts | 1 approved leave day in month → ≤1 → 5 pts | Manager rejected leave request (status=REJECTED) → 0 pts immediately
13 | Positive Behaviour | Behaviour & Reliability | 5 | MANUAL — Admin enters in KPI → Enter Monthly Scores metricId = 'positive_behaviour' options: 5 / 3 / 0 DEFAULT = 0 if not entered | 5 = Professional, punctual, zero late comings 3 = <3 minor late comings 0 = >3 lates or misconduct | Admin enters 5 (perfect conduct month) → 5 pts | Admin has not entered score yet → 0 pts (default)
GRADE THRESHOLDS & SCORE BREAKDOWN BY CATEGORY
Grade A — Excellent | 90 – 100 pts
Grade B — Good | 75 – 89 pts
Grade C — Average | 60 – 74 pts
Grade D — Poor | Below 60 pts
Delivery & Execution |  | 50 pts | Sprint(15) + Delivery(15) + Estimation(10) + Throughput(10)
Quality & Engineering Excellence |  | 20 pts | Rework(5) + Defect Leakage(10) + Engineering Hygiene(5)
Ownership & Collaboration |  | 10 pts | Dependency & Agile(5) + Reporting & Docs(5)
Growth & Innovation |  | 10 pts | Learning Velocity(5) + Automation & Innovation(5)
Behaviour & Reliability |  | 10 pts | Attendance(5) + Positive Behaviour(5)